## Planilha1
Feature	Task	Original Estimative	Current Estimative	Spent	Remaining	Done
Structs support	Decide syntax for writting to member	1	1	1	0	24/06/2022 01:25
Structs support	Decide syntax for reading from member	1	0	0	0	24/06/2022 01:25
Structs: Add type validation for writting to member	Decide value type	2	2	2	0	24/06/22 03:25
Structs: Add type validation for writting to member	Decide member type	2	0	0	0	24/06/22 03:25
Structs: Add type validation for writting to member	Check for match	1	0	0	0	24/06/22 03:25
Structs: Add type validation for writting to member	Decide back-end functions to base structs	2	2	0	2
Structs: Add type validation for writting to member	Rewrite __set__ to return back-end functions calling when writting to member	2	2	0	2
Debugging		8	8	0	8
Buffer		4	4	0	4
Structs: Add type validation for reading from member and setting to a variable	Decide member type	2	2	0	2
Structs: Add type validation for reading from member and setting to a variable	Decide name type (mut variables)	2	0	0	0
Structs: Add type validation for reading from member and setting to a variable	Check for match	1	0	0	0
Structs: Add type validation for reading from member and setting to a variable	Rewrite __eval__ to return back-end functions calling when reading from member	2	2	0	2
Debugging		8	8	0	8
Buffer		4	4	0	4
Structs: Initialization	Decide structs initialization syntax	2	2	0	2
Structs: Initialization	Check if all members were set (optional values won’t exist for now)	2	2	0	2
Structs: Initialization	Check for match between members and values types	4	4	0	4
Debugging		6	6	0	6
Buffer		2	2	0	2
Pointers support	Decide syntax for writting to pointer	1	1	0	1
Pointers support	Decide syntax for reading from pointer	1	1	0	1
Pointers support	Decide syntax to get pointer of variable	1	1	0	1
Pointers support	Decide back-end function to read from pointer	1	1	0	1
Pointers support	Decide back-end function to write to pointer	1	1	0	1
Debugging		4	4	0	4
Buffer		2	2	0	2
Unsafe blocks	Decide how unsafe will be implemented (switches on functions maybe?)	4	4	0	4
Unsafe blocks	Implement unsafe function/internal	4	4	0	4
Debugging		2	2	0	2
Buffer		2	2	0	2
Unbounded Polymorphism	Plan it	8	8	0	8
Unbounded Polymorphism	Implement unbound polymorphism	8	8	0	8
Debugging		8	8	0	8
Buffer		8	8	0	8
Pointers support	Write function/internal for writting to pointer (inside unsafe)	1	1	0	1
Pointers support	Write function/internal for reading from pointer (inside unsafe)	1	1	0	1
Pointers support: Arithmetic	Write function to add to a pointer	2	2	0	2
Debugging		4	4	0	4
Buffer		4	4	0	4
Name validation	Mut/const check at name setting	1	1	0	1
Name validation	Check for setting const uppon mut variables	2	2	0	2
Debugging		2	2	0	2
Buffer		1	1	0	1
ret support	Plan ret (are we going to “exit” and “goto”?)	2	2	0	2
ret support	Add ret function/internal	1	1	0	1
ret support	Get return value type	2	2	0	2
ret support	Check for match between return value type and function type	2	2	0	2
Debugging		4	4	0	4
Buffer		2	2	0	2
Hexadecimal numbers	Add syntax extension for hexadecimal numbers	2	2	0	2
Octal numbers	Add syntax extension for octal numbers	2	2	0	2
Binary numbers	Add syntax extension for binary numbers	2	2	0	2
Debugging		6	6	0	6
Buffer		4	4	0	4
Unlispyfication	Plan requisites	4	4	0	4
Unlispyfication	Add automatic parenthesis around lines	4	4	0	4
Unlispyfication	Add automatic parenthesis open at end of proper blocks	6	6	0	6
Debugging		14	14	0	14
Buffer		6	6	0	6
Write LLVM Back-End	Plan	4	4	0	4
Write LLVM Back-End	Change function returns to back-end palatable tree	6	6	0	6
Write LLVM Back-End	Add support for different tokens, internals and functions for our LISP	6	6	0	6
Debugging		16	16	0	16
Buffer		8	8	0	8
Write LLVM Back-End: Functions	Add function without arguments, without return type	4	4	0	4
Write LLVM Back-End: Functions	Add function with arguments, without return type	4	4	0	4
Write LLVM Back-End: Functions	Add function without arguments, with return type	4	4	0	4
Write LLVM Back-End: Functions	Add function with arguments, with return type	4	4	0	4
Debugging		16	16	0	16
Buffer		8	8	0	8
Write LLVM Back-End: Integers Addition		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers Subtraction		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers Multiplication		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Division		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Module		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Remainer		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Addition		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Subtraction		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Multiplication		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers > Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers >= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers < Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers <= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats > Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats >= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats < Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats <= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Bools == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Bools != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: If		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Tunning for amd64-linux		8	8	0	8
Debugging		8	8	0	8
Write LLVM Back-End: Print to stdout, stderr		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Receive arguments from command line		4	4	0	4
Debugging		4	4	0	4
Manual memory management support	Planning	8	8	0	8
Manual memory management support	alloc function	4	4	0	4
Manual memory management support	alloc function back-end	4	4	0	4
Debugging		4	4	0	4
Manual memory management support	free function	4	4	0	4
Manual memory management support	free function back-end	4	4	0	4
Debugging		4	4	0	4
Meta-test Exceptions		4	4	0	4
Debugging		4	4	0	4
		538	531	3	528