## Planilha1
Feature	Task	Original Estimative	Current Estimative	Spent	Remaining	Started	Done
Structs support	Decide syntax for writting to member	1	1	1	0		24/06/2022 01:25
Structs support	Decide syntax for reading from member	1	0	0	0		24/06/2022 01:25
Structs: Add type validation for writting to member	Decide value type	2	2	2	0		24/06/2022 03:25
Structs: Add type validation for writting to member	Decide member type	2	0	0	0		24/06/2022 03:25
Structs: Add type validation for writting to member	Check for match	1	0	0	0		24/06/2022 03:25
Structs: Add type validation for writting to member	Decide back-end functions to base structs	2	2	0	2
Structs: Add type validation for writting to member	Rewrite __set__ to return back-end functions calling when writting to member	2	2	0	2
Debugging		8	2	0	2
Buffer		4	0	0	0
Structs: Add type validation for reading from member and setting to a variable	Decide member type	2	2	1,25	0,75	24/06/2023 11:18	24/06/2023 12:32
Structs: Add type validation for reading from member and setting to a variable	Decide name type (mut variables)	2	0	0	0	24/06/2023 11:18	24/06/2023 12:32
Structs: Add type validation for reading from member and setting to a variable	Check for match	1	0	0	0	24/06/2023 11:18	24/06/2023 12:32
Structs: Add type validation for reading from member and setting to a variable	Rewrite __eval__ to return back-end functions calling when reading from member	2	0	0	0	24/06/2023 11:18	24/06/2023 12:32
Debugging		8	0	0	0
Buffer		4	2	0	2
Structs: Initialization	Decide structs initialization syntax (??? we’re already initializing structs anyway)	2	0	0	0
Structs: Initialization	Check if all members were set (optional values won’t exist for now)	2	2	2	0	24/06/2023 14:54	24/06/2023 16:45
Structs: Initialization	Check for match between members and values types	4	0	0	0	24/06/2023 14:54	24/06/2023 16:45
Debugging		6	3	0	3
Buffer		2	0	0	0
Default functions support	Add support for default functions	2	0	0	0	26/06/23 23:20	?
Functions	Make argument names work inside function scope	3	3	1,3	1,7	28/06/2023 19:40	28/06/2023 21:00
Pointers support + Internal masking	Add support for functions taking ids as arguments	2	0	1	-1	26/06/23 23:20
Pointers support	Decide syntax for writting to pointer: write (ptr int 0x0) 0	1	0	1	-1	?	25/06/2023 02:29
Pointers support	Decide syntax for reading from pointer: read (ptr int 0x0)	1	0	0	0	?	25/06/2023 02:29
Pointers support	Decide syntax to get pointer of variable: get ptr myvar	1	0	0	0	?	25/06/2023 02:29
Pointers support	Decide back-end function to read from pointer: read_ptr	1	0	0	0	?	25/06/2023 02:29
Pointers support	Decide back-end function to write to pointer: write_ptr	1	0	0	0	?	25/06/2023 02:29
Pointers support	Decide back-end function to get pointer of variable: get_ptr	1	0	0	0	?	25/06/2023 02:29
Pointers support + Internal masking	Mask read_ptr	1	0	0	0
Pointers support + Internal masking	Mask write_ptr	1	0	0	0
Pointers support + Internal masking	Mask get_ptr	1	0	0	0
Pointers support	sizeof back-end function	2	0	0	0
Pointers support	offset back-end function for struct members (struct member access isn’t enough for the back-end to understand?)	2	0	0	0
Debugging		4	4	0	4
Buffer		2	7	0	7
Unsafe blocks	Decide how unsafe will be implemented (switches on functions maybe?)	4	2	0,6	1,4	28/06/23 23:10	28/06/23 23:50
Unsafe blocks	Implement unsafe function/internal	4	0	0	0
Debugging		2	2	0	2
Buffer		2	2	0	2
Polymorphism	Plan it	8	0	0	0
Polymorphism	Implement unbound polymorphism	8	0	0	0
Debugging		8	0	0	0
Buffer		8	0	0	0
Pointers support	Write function/internal for writting to pointer (inside unsafe)	1	2	0	2
Pointers support	Write function/internal for reading from pointer (inside unsafe)	1	0	0	0
Pointers support: Arithmetic	Write function to add to a pointer	2	0	0	0
Pointers support: Arithmetic	Write function to subtract from a pointer	2	0	0	0
Debugging		4	0	0	0
Buffer		4	0	0	0
Name validation	Mut/const check at name setting	1	1	0,25	0,75	30/06/23 22:35	30/06/23 22:45
Name validation	Check for setting const upon mut variables	2	1	0,25	0,75	30/06/23 23:00	30/06/23 23:15
Debugging		2	2	0	2
Buffer		1	1	0	1
ret support	Add ret function/internal	2	3	0	3	02/07/23 15:45	02/07/23 23:25
Debugging		4	4	0	4
Buffer		2	2	0	2
goto support	Plan goto (maybe make it implicit)	1	1	0	1
goto support	Add goto function/internal	2	2	0	2
Debugging		3	3	0	3
Buffer		1	1	0	1
Exit + handle support	Plan exit + handle	2	2	2	0		09/07/23 01:45
Exit + handle support	Add exit (added second value in return)	2	2	2	0		09/07/23 01:45
Exit + handle support	Add handle	2	0	0	0		09/07/23 01:45
Exit + handle support	Add panic	2	2	0	2
Debugging		6	6	0	6
Buffer		2	2	0	2
Hexadecimal numbers	Add syntax extension for hexadecimal numbers (low level representation don’t need to change lisp)	2	2	0	2
Octal numbers	Add syntax extension for octal numbers	2	1	0	1
Binary numbers	Add syntax extension for binary numbers	2	1	0	1
Debugging		6	2	0	2
Buffer		4	2	0	2
if support	(Comparison requires implementation of low level operation)	2	2	0	2
Debugging		2	2	0	2
Buffer		2	2	0	2
let support	(Functions can already be defined and called, só no need for let and this already makes possible recursive functions)	2	2	0	2
Debugging		2	2	0	2
Buffer		2	2	0	2
Unlispyfication	Plan requisites	4	4	4	0		09/07/2023 02:35
Unlispyfication	Add automatic parenthesis around lines	4	4	4	0
Unlispyfication	Add automatic parenthesis open at end of proper blocks	6	6	6	0		21/07/2023 22:00 – done other things as well
Debugging		14	8	0	8
Buffer		6	4	0	4
Write LLVM Back-End	Plan	4	4	0	4	21/07/23 22:00
Write LLVM Back-End	Change function returns to back-end palatable tree	6	6	0	6
Write LLVM Back-End	Move “default scope" to run.py
Write LLVM Back-End	Add support for different tokens, internals and functions for our LISP	6	6	0	6
Debugging		16	16	0	16
Buffer		8	8	0	8
Write LLVM Back-End: Functions	Add function without arguments, without return type	4	4	0	4
Write LLVM Back-End: Functions	Add function with arguments, without return type	4	4	0	4
Write LLVM Back-End: Functions	Add function without arguments, with return type	4	4	0	4
Write LLVM Back-End: Functions	Add function with arguments, with return type	4	4	0	4
Debugging		16	16	0	16
Buffer		8	8	0	8
Write LLVM Back-End: Integers Addition		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers Subtraction		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers Multiplication		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Division		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Module		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Remainer		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Addition		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Subtraction		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Multiplication		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers > Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers >= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers < Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers <= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats > Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats >= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats < Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats <= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Bools == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Bools != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: If		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Tunning for amd64-linux		8	8	0	8
Debugging		8	8	0	8
Actions		2	2	0	2
Debugging		2	2	0	2		24/09/23 13:27
Separate function arguments using commas		1	1	1	0
Fix array declaration		2	2	2	0
Constant propagation to global Space in LLVM IR		2					12/10/23 00:38
Turn scope into a dict							13/10/23 02:06
Remove forced_handler from scope and handler instances		1					13/10/23 02:15
Separate set and fn		2					13/10/13 17:31
Add “stop at error” flag to tests							15/10/13 15:30
Add autoclean to test/run							15/10/13 15:30
Fix DEBUG							15/10/13 17:10
Separate set and reassignment		2					19/10/13 00:41
Change order of name and type in set
Change order of name and mutdecl in set
Change “internals” to “builtins”		1
Add “_invalid” to test names		1					19/10/13 01:00
Bin function							30/10/23 00:00
Clean eval, add hooks							01/11/23 22:17
Clean find_function_method, get internals out of it							01/11/23 22:51
Tailcall
Add check for spaces at beginning of lines							02/11/23 01:06
Check bug in get_element_value for functions set in different scopes
Array get member
Array bounds checks
Struct backend support	Definition
Struct backend support	Initialization
Struct backend support	Set member
Struct backend support	Get member
Function definitions	Allow declaring functions in any order
Functions inside functions
Generic types	Definition
Generic types	Initialization
Generic types	Functions
Kinds	Definition
Kinds	Implementation
Kinds	Functions
Integer types
Float types
Result type
Option type
Unique Types	Definition
	Marking in scope
	Drop
Write LLVM Back-End: Print to stdout, stderr		4	4	0	4
Debugging		4	4	0	4
Files	Open files
	Close files
	Read from files
	File Struct
Manual memory management support	Planning	8	8	0	8
Manual memory management support	alloc function	4	4	0	4
Manual memory management support	alloc function back-end	4	4	0	4
Manual memory management support	free function	4	4	0	4
Manual memory management support	free function back-end	4	4	0	4
Dynamic Arrays	Definition

Dynamic Strings	Definition
	Formatting
Linked Lists
Dicts
Write LLVM Back-End: Receive arguments from command line

Compiler errors
Processes
Shell exec

		577	448	31,65	416,35
		12h Weeks	12h Weeks
		48,0833333333333	37,3333333333333
			Guesstimate
			300
			25
			6,25