## Planilha1
Feature	Task	Original Estimative	Current Estimative	Spent	Remaining	Started	Done
Structs support	Decide syntax for writting to member	1	1	1	0		24/06/2022 01:25
Structs support	Decide syntax for reading from member	1	0	0	0		24/06/2022 01:25
Structs: Add type validation for writting to member	Decide value type	2	2	2	0		24/06/2022 03:25
Structs: Add type validation for writting to member	Decide member type	2	0	0	0		24/06/2022 03:25
Structs: Add type validation for writting to member	Check for match	1	0	0	0		24/06/2022 03:25
Structs: Add type validation for writting to member	Decide back-end functions to base structs	2	2	0	2
Structs: Add type validation for writting to member	Rewrite __set__ to return back-end functions calling when writting to member	2	2	0	2
Debugging		8	2	0	2
Buffer		4	0	0	0
Structs: Add type validation for reading from member and setting to a variable	Decide member type	2	2	1,25	0,75	24/06/2023 11:18	24/06/2023 12:32
Structs: Add type validation for reading from member and setting to a variable	Decide name type (mut variables)	2	0	0	0	24/06/2023 11:18	24/06/2023 12:32
Structs: Add type validation for reading from member and setting to a variable	Check for match	1	0	0	0	24/06/2023 11:18	24/06/2023 12:32
Structs: Add type validation for reading from member and setting to a variable	Rewrite __eval__ to return back-end functions calling when reading from member	2	0	0	0	24/06/2023 11:18	24/06/2023 12:32
Debugging		8	0	0	0
Buffer		4	2	0	2
Structs: Initialization	Decide structs initialization syntax (??? we’re already initializing structs anyway)	2	0	0	0
Structs: Initialization	Check if all members were set (optional values won’t exist for now)	2	2	2	0	24/06/2023 14:54	24/06/2023 16:45
Structs: Initialization	Check for match between members and values types	4	0	0	0	24/06/2023 14:54	24/06/2023 16:45
Debugging		6	3	0	3
Buffer		2	0	0	0
Default functions support	Add support for default functions	2	0	0	0	26/06/23 23:20	?
Functions	Make argument names work inside function scope	3	3	1,3	1,7	28/06/2023 19:40	28/06/2023 21:00
Pointers support + Internal masking	Add support for functions taking ids as arguments	2	0	1	-1	26/06/23 23:20
Pointers support	Decide syntax for writting to pointer: write (ptr int 0x0) 0	1	0	1	-1	?	25/06/2023 02:29
Pointers support	Decide syntax for reading from pointer: read (ptr int 0x0)	1	0	0	0	?	25/06/2023 02:29
Pointers support	Decide syntax to get pointer of variable: get ptr myvar	1	0	0	0	?	25/06/2023 02:29
Pointers support	Decide back-end function to read from pointer: read_ptr	1	0	0	0	?	25/06/2023 02:29
Pointers support	Decide back-end function to write to pointer: write_ptr	1	0	0	0	?	25/06/2023 02:29
Pointers support	Decide back-end function to get pointer of variable: get_ptr	1	0	0	0	?	25/06/2023 02:29
Pointers support + Internal masking	Mask read_ptr	1	0	0	0
Pointers support + Internal masking	Mask write_ptr	1	0	0	0
Pointers support + Internal masking	Mask get_ptr	1	0	0	0
Pointers support	sizeof back-end function	2	0	0	0
Pointers support	offset back-end function for struct members (struct member access isn’t enough for the back-end to understand?)	2	0	0	0
Debugging		4	4	0	4
Buffer		2	7	0	7
Unsafe blocks	Decide how unsafe will be implemented (switches on functions maybe?)	4	2	0,6	1,4	28/06/23 23:10	28/06/23 23:50
Unsafe blocks	Implement unsafe function/internal	4	0	0	0
Debugging		2	2	0	2
Buffer		2	2	0	2
Polymorphism	Plan it	8	0	0	0
Polymorphism	Implement unbound polymorphism	8	0	0	0
Debugging		8	0	0	0
Buffer		8	0	0	0
Pointers support	Write function/internal for writting to pointer (inside unsafe)	1	2	0	2
Pointers support	Write function/internal for reading from pointer (inside unsafe)	1	0	0	0
Pointers support: Arithmetic	Write function to add to a pointer	2	0	0	0
Pointers support: Arithmetic	Write function to subtract from a pointer	2	0	0	0
Debugging		4	0	0	0
Buffer		4	0	0	0
Name validation	Mut/const check at name setting	1	1	0,25	0,75	30/06/23 22:35	30/06/23 22:45
Name validation	Check for setting const upon mut variables	2	1	0,25	0,75	30/06/23 23:00	30/06/23 23:15
Debugging		2	2	0	2
Buffer		1	1	0	1
ret support	Add ret function/internal	2	3	0	3	02/07/23 15:45	02/07/23 23:25
Debugging		4	4	0	4
Buffer		2	2	0	2
goto support	Plan goto (maybe make it implicit)	1	1	0	1
goto support	Add goto function/internal	2	2	0	2
Debugging		3	3	0	3
Buffer		1	1	0	1
Exit + handle support	Plan exit + handle	2	2	2	0		09/07/23 01:45
Exit + handle support	Add exit (added second value in return)	2	2	2	0		09/07/23 01:45
Exit + handle support	Add handle	2	0	0	0		09/07/23 01:45
Exit + handle support	Add panic	2	2	0	2
Debugging		6	6	0	6
Buffer		2	2	0	2
Hexadecimal numbers	Add syntax extension for hexadecimal numbers (low level representation don’t need to change lisp)	2	2	0	2
Octal numbers	Add syntax extension for octal numbers	2	1	0	1
Binary numbers	Add syntax extension for binary numbers	2	1	0	1
Debugging		6	2	0	2
Buffer		4	2	0	2
if support	(Comparison requires implementation of low level operation)	2	2	0	2
Debugging		2	2	0	2
Buffer		2	2	0	2
let support	(Functions can already be defined and called, só no need for let and this already makes possible recursive functions)	2	2	0	2
Debugging		2	2	0	2
Buffer		2	2	0	2
Unlispyfication	Plan requisites	4	4	4	0		09/07/2023 02:35
Unlispyfication	Add automatic parenthesis around lines	4	4	4	0
Unlispyfication	Add automatic parenthesis open at end of proper blocks	6	6	6	0		21/07/2023 22:00 – done other things as well
Debugging		14	8	0	8
Buffer		6	4	0	4
Write LLVM Back-End	Plan	4	4	0	4	21/07/23 22:00
Write LLVM Back-End	Change function returns to back-end palatable tree	6	6	0	6
Write LLVM Back-End	Move “default scope" to run.py
Write LLVM Back-End	Add support for different tokens, internals and functions for our LISP	6	6	0	6
Debugging		16	16	0	16
Buffer		8	8	0	8
Write LLVM Back-End: Functions	Add function without arguments, without return type	4	4	0	4
Write LLVM Back-End: Functions	Add function with arguments, without return type	4	4	0	4
Write LLVM Back-End: Functions	Add function without arguments, with return type	4	4	0	4
Write LLVM Back-End: Functions	Add function with arguments, with return type	4	4	0	4
Debugging		16	16	0	16
Buffer		8	8	0	8
Write LLVM Back-End: Integers Addition		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers Subtraction		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers Multiplication		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Division		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Module		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Remainer		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Addition		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Subtraction		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats Multiplication		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers > Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers >= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers < Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Integers <= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats > Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats >= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats < Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Floats <= Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Bools == Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Bools != Comparison		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: If		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Tunning for amd64-linux		8	8	0	8
Debugging		8	8	0	8
Actions		2	2	0	2
Debugging		2	2	0	2		24/09/23 13:27
Separate function arguments using commas		1	1	1	0
Fix array declaration		2	2	2	0
Constant propagation to global Space in LLVM IR		2					12/10/23 00:38
Remove forced_handler from scope and handler instances		1
Separate set and fn		2
Separate set and reassignment		2
Change order of name and type in set
Change order of name and mutdecl in set
Turn scope into a dict		1
Change “internals” to “builtins”		1
Add “_invalid” to test names		1
Fix DEBUG		2
Add “stop at error” flag to tests
Add autoclean to test/run
Add check for spaces at beginning of lines
Check bug in get_element_value for functions set in different scopes

Write LLVM Back-End: Print to stdout, stderr		4	4	0	4
Debugging		4	4	0	4
Write LLVM Back-End: Receive arguments from command line		4	4	0	4
Debugging		4	4	0	4

Manual memory management support	Planning	8	8	0	8
Manual memory management support	alloc function	4	4	0	4
Manual memory management support	alloc function back-end	4	4	0	4
Debugging		4	4	0	4
Manual memory management support	free function	4	4	0	4
Manual memory management support	free function back-end	4	4	0	4
Debugging		4	4	0	4
Meta-test Exceptions		4	4	0	4
Debugging		4	4	0	4
		604	472	31,65	440,35
		12h Weeks	12h Weeks
		50,3333333333333	39,3333333333333
			Guesstimate
			300
			25
			6,25